## Yearly
| Setup | CI | CD | Docu | Difficulty
April | Project Plan |  |  |  | Easy
May | Create infrastructure |  |  |  | Medium
| Create code | GitHub Actions | Azure Pipeline |  | Hard
June |  |  |  | Create Docu
| Goals | Goals | Goals | Goals
| Create a complete Project plan | Create CI | Create CD | Create Docu
Setup the whole infrastructure in Azure and GitHub
Create application code

## Quaterly
| Setup | CI | CD | Docu | Difficulty
Q2 2023 | Project Plan | GitHub Actions | Azure Pipeline | Create Docu | Easy
| Create infrastructure |  |  |  | Medium
| Create code |  |  |  | Hard
| Goals | Goals | Goals | Goals
| Create a complete Project plan | Create CI | Create CD | Create Docu
Setup the whole infrastructure in Azure and GitHub
Create application code

## Weekly
Month | Weekt | Setup | CI | CD | Docu
Mai | KW 17 | Project Plan
| KW 18 | Create Azure Infrastructure |  |  |  | Difficulty
| KW 19 | Create Azure Infrastructure |  |  |  | Easy
| KW 20 | Create GitHub Infrastructure |  |  |  | Medium
| KW 21 | Create GitHub Infrastructure |  |  |  | Hard
Juni | KW 22 | Create code
| KW 23 |  | GitHub Actions
| KW 24 |  |  | Azure Pipeline
| KW 25 |  |  | Azure Pipeline
July | KW 26 |  |  |  | Create Docu
| KW 27 |  |  |  | Create Docu
|  | Goals | Goals | Goals | Goals
|  | Create a complete Project plan | Create CI | Create CD | Create Docu
Setup the whole infrastructure in Azure and GitHub
Create application code